## Sheet1
ID | Name | Estimate Duration | Description
1 | PM Documentation | 6 Months | Generate PM documentation
001a | Project Charter | -
001b | Requirements Analysis | -
001c | Scope Management Plan | -
001d | Work Breakdown Structure | -
001e | Stakeholder Management | -
001f | Management Methodology | -
2 | Critical Stakeholder Approval | 3 Months | Gain the approval of stakeholder
002a | Local Indigenous Community | -
002b | Civil Aviation Security Authority (CASA) | -
002c | Australian Defence Force (ADF) | -
3 | Design Finalisation | 1 Year | Finalise Technical Designs
003a | Electrical
003b | Structural
003c | Environmental
003d | Software
4 | Site Construction | 1.5 Years | Complete Site Construction
004a | Foundation Reinforcement | -
004b | Transport Links & Roads | -
004c | Utility Access | -
004d | Tracking Facility | -
5 | Site Testing | 6 Months | Test Facility Functionality
005a | Software test | -
005b | Transport testing | -
005c | Launch Test | -
6 | Site Handover | 3 Months | Closing
| TOTAL | 4 years